## Backlog
BLACKLOG - STRANGER THINGS
Rank | Story | Story Points | Release # | Business Value | Change Management Notes (comments relating to a story point chaning, new story added or a story removed)
APLICATIVO WEB
1 - Informacion de la Saga
1 | 1.1 Creacion Index | 4 | 1 | High
1.2 Creacion vistas
2 | 1.2 Creacion Personajes | 3 | 1 | High
3 | 1.3 Creacion Sinopsis Episodios | 3 | 1 | Medium
2 - Informacion Banda Sonora
1 | 2.1 Creacion banda sonora | 2 | 2 | Medium
2 | 2.2 Creacion vistas
3 - Lista de Premios de la Serie
1 | 3.1 Creacion Premios | 3 | 3 | High
2 | 3.2 Creacion vistas
4 - Libros Oficiales
1 | 4.1 Creacion Libros | 2 | 4 | High
2 | 4.2 Creacion vistas
5 - Como usuario quiero registrarme
1 | 5.1 Registrarme atravez de un formulario | 2 | 1 | High
2 | 5.2 Recuperacion de Contraseña | 2 | 1
3 | 5.3 Verificacion por correo | 2 | 2
6- Mantenimiento
1 | 6.1 Realizar Prueba a las vistas | 2 | 1 | High
2 | 6.2 Realizar pruebas a las bases de datos | 2 | 1
7- No funcionales
1 | 7.1 Instalar motor de base de datos | 2 | 1 | High
2 | 7.2 Instalar algun sistema operativo | 2 | 1
3 | 7.3 Presentar diagrama de arquitectura | 2 | 1
4 | 7.4 Documento con la codificacion | 2 | 1
| Original Story Points for Release 1 | 35
New Points for Release 1
| Total Points for Release 1 | 35 | 0% |  | Change in scope

## Capacity Planning
| Resource Capacity By Iteration |  |  |  | From | To | Working Days: |  | From | To | Working Days: |  | From | To | Working Days: |  | From | To | Working Days:
[5 empty] | 2022-08-01 | 2022-08-07 | 7 |  | 2022-08-08 | 2022-08-14 | 7 |  | 2022-08-15 | 2022-08-21 | 7 |  | 2022-08-22 | 2022-09-04 | 14
|  |  |  | Iteration 1 |  |  |  | Iteration 2 |  |  |  | Iteration 3 |  |  |  | Iteration 4
Resource Type | Core Team | Resource Names | % Allocation | # Days Off | Available Hrs | Planned Hrs | % Utilization | # Days Off | Available Hrs | Planned Hrs | % Utilization | # Days Off | Available Hrs | Planned Hrs | % Utilization | # Days Off | Available Hrs | Planned Hrs | % Utilization
Employee | Engineer 1 Fronted | Michael Lopez | 100% | 1 | 48 | 35 | 72.92% | 1 | 48 | 30 | 62.5% | 2 | 40 | 30 | 75% | 2 | 96 | 54 | 56.25%
Employee | Engineer 2 Backend | Michael Cardenas | 100% | 1 | 48 | 35 | 72.92% | 2 | 40 | 30 | 75% | 1 | 48 | 30 | 62.5% | 2 | 96 | 30 | 31.25%
Employee | QA Tester | Andres Lopez | 75% | 1 | 34 | 20 | 58.82% | 1 | 34 | 10 | 29.41% | 2 | 26 | 26 | 100% | 2 | 68 | 35 | 51.47%
Contractor | Scrum Master | Andres Cardenas | 80% | 1 | 36.8 | 30 | 81.52% | 2 | 28.8 | 20 | 69.44% | 1 | 36.8 | 30 | 81.52% | 2 | 73.6 | 35 | 47.55%
Employee | Product Owner | Andres Lopez | 40% | 1 | 14.4 | 7 | 48.61% | 1 | 14.4 | 10 | 69.44% | 2 | 6.4 | 3 | 46.87% | 2 | 28.8 | 15 | 52.08%
Employee | Ula | Michael Andres | 50% | 1 | 20 | 2 | 10% | 2 | 12 | 4 | 33.33% | 1 | 20 | 5 | 25% | 2 | 40 | 10 | 25%
Listing the team members here and their contact information is helpful plus their allocation and planned days off is very useful. Using the iteration capacity and utilization planning is optional and could be used if the team finds it useful for them to plan their work. The best method for determining capacity is looking at previous velocity then adjusting for vacation or holidays.
Email me if you have questions about what the data in this worksheet means. Sally@AgileTraining.com
Iteration Capacity Map Worksheet
Use the table below to map out each story into the sub-deliverables (tasks/milestones) through the course of your iteration so you can plan your capacity and commitements better as a team. Color code the different type of work (req, desgin, dev, testing, uat..). This is best done on a physical visible wall.
| Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11
Iteration #: 5 (2 wks)
Stories | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 As a manager I want to .. So that..
1.2 As a supervisor I want to .. So that..
Velocity Avg by Team
|  |  | Team A | Team B | Team C | Team D
|  | Q1 | 475 | 200 | 350 | 150
|  | Q2 | 400 | 250 | 390 | 230
|  | Q3 | 435 | 275 | 425 | 200
|  | Q4 | 450 | 260 | 400 | 245
|  | Yearly | 1760 | 985 | 1565 | 825
Design and Code TC1,2,3 - AJ
Test TC1, TC2
- Shri
UAT TC1,2,3
Design and Code TC4-6 - AJ
Update Req/UAT Doc - Jen
Test TC1, TC2
- Shri
UAT TC4,5,6
Deploy
Deploy
Design Review
Automate xyz
- Lilly
UAT xyz
Design and Code xyz - Adam
Update Req/UAT Doc - Jen
Test abc - Shri
UAT abc
Deploy
Deploy
Code abc - Adam
Sprint Review and Final Acceptance
Sprint Demo & Retrospective | Sprint Planning
Note on G4: Sally: identified during planning meeting
Note on K4: Sally: identified during planning meeting
Note on O4: Sally: identified during planning meeting
Note on S4: Sally: identified during planning meeting

## Release Plan
Setup Iteration
| STORIES | STORY POINTS | Owner |  | STORY GOAL
[5 empty] | Target | Actual
| 1.1 Creacion Index | 4
| 1.2 Creacion Personajes | 3
| 1.3 Creacion Sinopsis Episodios | 3
| 2.1 Creacion banda sonora | 2
| 3.1 Creacion Premios | 3
| 4.1 Creacion Libros | 2
| 5.1 Creacion Registros | 4
Setup Iteration Story Points |  |  |  | Iteration | 0 | 0
|  |  |  | Cumulative | 0 | 0
Iteration Cost |  |  |  | Iteration | 90000 | 85000
|  |  |  | Cumulative | 90000 | 85000
ITERATION 1 (August 01 - August 07)
| STORIES | STORY POINTS | Owner |  | STORY GOAL
[5 empty] | Target | Actual
| 1.1 Creacion Index | 4 | MICHAEL LOPEZ |  | DONE | DONE
| 1.1 Creacion Index | 4 | MICHAEL LOPEZ |  | DONE | DONE
| 1.2 Creacion Personajes | 3 | MICHAEL LOPEZ |  | NOT DONE | NOT DONE
Iteration #1 Story Points |  |  |  | Iteration | 8 | 8
|  |  |  | Cumulative | 8 | 8
Iteration Cost |  |  |  | Iteration | 90000 | 93000
|  |  |  | Cumulative | 180000 | 178000
ITERATION 2 (August 08 - August 14)
| STORIES | STORY POINTS | Owner |  | STORY GOAL
[5 empty] | Target | Actual
| 1.2 Creacion Personajes | 3 | MICHAEL LOPEZ |  | DONE | NOT DONE
| 1.3 Creacion Sinopsis Episodios | 3 | MICHAEL LOPEZ |  | DONE | NOT DONE
Iteration #2 Story Points |  |  |  | Iteration | 6 | 0
|  |  |  | Cumulative | 14 | 8
Iteration Cost |  |  |  | Iteration | 90000 | 110000
|  |  |  | Cumulative | 270000 | 288000
ITERATION 3 (August 15 - August 21)
| STORIES | STORY POINTS | RESOURCES |  | STORY GOAL
[5 empty] | Target | Actual
| 5.1 Creacion Registros | 4 | MICHAEL LOPEZ |  | DONE | DONE
| 1.3 Creacion Sinopsis Episodios | 3 | MICHAEL LOPEZ |  | DONE | DONE
| 4.1 Creacion Libros | 2 | MICHAEL LOPEZ |  | DONE | DONE
Iteration #3 Story Points |  |  |  | Iteration | 9 | 9
|  |  |  | Cumulative | 23 | 17
Iteration Cost |  |  |  | Iteration | 90000 | 120000
|  |  |  | Cumulative | 360000 | 408000
ITERATION 4 (August 22- September 04)
| STORIES | STORY POINTS | Owner |  | STORY GOAL
[5 empty] | Target | Actual
| 2.1 Creacion banda sonora | 2 | MICHAEL LOPEZ |  | DONE | DONE
| 3.1 Creacion Premios | 3 | MICHAEL LOPEZ |  | DONE
Iteration #4 Story Points |  |  |  | Iteration | 5 | 2
|  |  |  | Cumulative | 28 | 19
Iteration Cost |  |  |  | Iteration | 90000 | 80000
|  |  |  | Cumulative | 450000 | 488000
Sept 23rd - Oct 7th
Hardening Iteration (Regression / Integration /Performance/Beta Testing )
Pre-Release Iteration (Oct 7th - Oct 28th)
PRODUCTION | FINAL USER TRAINING PROJECT TRANSITION HELP DOCUMENTATION REGRESSION AND INTEGRATION TESTING USER ACCEPTANCE & SIGNGOFF
Iteration Cost |  |  |  | Iteration | 90000 | 80000
|  |  |  | Cumulative | 540000 | 568000
2011-10-31
Move to Production